## CodeGen_Optimizer_Reqs
POD | Data Engineering Hub - Code Generator & Optimizer
Agent Name | DE_CodeGen_Optimizer_Agent
Owner | Rakesh + Elan + Vamsee
Resources | Varun, Sanay
Description | Generate production-ready data engineering code (SQL, PySpark, dbt, Airflow) from approved designs, optimize for performance & cost, and produce deployment-ready artifacts with documentation.
# | Requirements Description | In Scope / Out of Scope | Dependency Requirement # | LOE (High/ Med / LOW) | MVP (1-4) | Planned St.Dt | Planned End Dt | Comments
INPUT PARSING & CONTEXT UNDERSTANDING
req_cg_001 | Consume approved data model output (ERD, table DDL, column specs) from the Data Design POD agent and parse into structured internal representation. | In Scope | Data_Design req_002 | High | 1 |  |  | Core entry point; must handle JSON/YAML/markdown model output
req_cg_002 | Consume approved pipeline architecture (batch/streaming/lakehouse pattern, component breakdown) from Data Design POD agent. | In Scope | Data_Design req_003 | High | 1 |  |  | Includes data flow diagrams, source-target mapping
req_cg_003 | Parse and load approved tech-stack recommendations (tool choices, platform constraints) to inform code generation target. | In Scope | Data_Design req_004 | Med | 1 |  |  | Determines whether output is Spark, SQL, dbt, Airflow, etc.
req_cg_004 | Accept user-provided business rules, transformation logic, and edge-case specifications as supplementary input. | In Scope |  | Med | 2 |  |  | Free-text or structured YAML; agent extracts actionable rules
req_cg_005 | Accept optional sample data or schema-level statistics (row counts, cardinality, null rates) to guide optimization decisions. | In Scope |  | Low | 3 |  |  | Used by optimizer for join strategy, partitioning decisions
req_cg_006 | Parse requirements documents or Jira stories directly to extract transformation intent when formal design artifacts are not yet available. | Out of Scope | [5 empty] | Deferred — requires NLP layer; design POD output is the source of truth for MVP
CODE GENERATION ENGINE
req_cg_007 | Generate SQL DDL statements (CREATE TABLE, ALTER TABLE) for target platform (Snowflake, BigQuery, Redshift, Databricks) from the parsed data model. | In Scope | req_cg_001 | High | 1 |  |  | Platform-specific syntax: clustering keys, sort keys, partitioning clauses
req_cg_008 | Generate SQL DML / transformation queries (SELECT, INSERT, MERGE/UPSERT) implementing source-to-target mapping and transformation logic. | In Scope | req_cg_001, req_cg_002 | High | 1 |  |  | Handles SCD Type-1/2, incremental loads, full refresh patterns
req_cg_009 | Generate PySpark transformation scripts for large-scale or streaming workloads where SQL is insufficient. | In Scope | req_cg_002, req_cg_003 | High | 2 |  |  | Structured Streaming, DataFrame API, UDFs where needed
req_cg_010 | Generate dbt model files (.sql) with proper ref() / source() macros, schema.yml tests, and documentation blocks. | In Scope | req_cg_001, req_cg_003 | High | 1 |  |  | Follows dbt best practices: staging > intermediate > marts layering
req_cg_011 | Generate Airflow DAG definitions (Python) with correct task dependencies, retry logic, SLA monitoring, and parameterized scheduling. | In Scope | req_cg_002 | High | 2 |  |  | TaskFlow API preferred; includes sensor tasks for data availability
req_cg_012 | Generate data quality check code (Great Expectations suites, dbt tests, or custom SQL assertions) aligned to Testing POD scope categories. | In Scope | req_cg_008, Testing POD | Med | 2 |  |  | Schema validation, null checks, referential integrity, row count reconciliation
req_cg_013 | Support multi-dialect code generation — same logical transformation renderable in Snowflake SQL, BigQuery SQL, Spark SQL, and PySpark. | In Scope | req_cg_003 | High | 3 |  |  | Dialect adapter pattern; MVP can start with 1 dialect, expand later
req_cg_014 | Generate CI/CD pipeline configuration (GitHub Actions / GitLab CI YAML) for automated testing and deployment of generated code. | Out of Scope | [5 empty] | Deferred to DevOps integration phase; manual deployment for MVP
req_cg_015 | Generate infrastructure-as-code (Terraform, Pulumi) for provisioning data platform resources. | Out of Scope | [5 empty] | Out of scope — infrastructure provisioning is a separate concern
CODE OPTIMIZATION ENGINE
req_cg_016 | Analyze generated SQL for performance anti-patterns: SELECT *, unnecessary subqueries, missing predicates, Cartesian joins, non-sargable WHERE clauses. | In Scope | req_cg_008 | High | 1 |  |  | Rule-based static analysis + LLM-guided suggestions
req_cg_017 | Recommend and apply partitioning strategy (date, hash, range) based on table size estimates and common query patterns. | In Scope | req_cg_005, req_cg_007 | High | 2 |  |  | Uses cardinality/volume hints from input; defaults to date partition if unknown
req_cg_018 | Recommend and apply clustering / sort key strategy for columnar stores (Snowflake clustering keys, BigQuery clustering, Redshift sort keys). | In Scope | req_cg_007 | Med | 2 |  |  | Based on anticipated join keys and filter columns
req_cg_019 | Optimize JOIN order and strategy (broadcast vs. shuffle, hash vs. sort-merge) for PySpark transformations based on estimated data volumes. | In Scope | req_cg_009 | High | 2 |  |  | Adds broadcast hints, repartition calls where beneficial
req_cg_020 | Detect and eliminate redundant transformations, unnecessary materializations, and duplicate computation across pipeline stages. | In Scope | req_cg_008, req_cg_009 | Med | 3 |  |  | DAG-level optimization: prune unused columns early, combine filters
req_cg_021 | Estimate query cost (compute credits / slot-hours) and flag expensive operations with cheaper alternatives. | In Scope |  | Med | 3 |  |  | Heuristic-based; platform-specific cost model approximations
req_cg_022 | Auto-tune Spark configurations (executor memory, shuffle partitions, AQE settings) based on workload profile. | Out of Scope | [5 empty] | Requires runtime profiling data; deferred to future runtime-feedback loop
req_cg_023 | Integrate with query execution plans (EXPLAIN output) from live warehouse to validate optimization recommendations. | Out of Scope | [5 empty] | Requires live warehouse connectivity; MVP operates on static analysis only
CODE QUALITY & STANDARDS
req_cg_024 | Enforce consistent naming conventions across all generated code: snake_case for columns/tables, prefixed layer names (stg_, int_, fct_, dim_). | In Scope |  | Med | 1 |  |  | Configurable naming rules via YAML config file
req_cg_025 | Generate inline comments and header documentation blocks for every generated file explaining purpose, source, target, SCD type, and refresh strategy. | In Scope |  | Med | 1 |  |  | Standardized header template with metadata
req_cg_026 | Apply SQL formatting standards (consistent indentation, keyword casing, comma placement) using sqlfluff-compatible rules. | In Scope |  | Low | 2 |  |  | Configurable style: leading commas vs trailing, uppercase keywords etc.
req_cg_027 | Generate a code manifest / inventory listing all generated files, their purpose, dependencies, and execution order. | In Scope |  | Low | 2 |  |  | Markdown or JSON manifest for handoff to deployment
req_cg_028 | Ensure all generated code handles NULL values explicitly — no implicit NULL propagation in joins, aggregations, or filters. | In Scope |  | Med | 1 |  |  | COALESCE wrappers, IS NOT NULL guards in JOINs
req_cg_029 | Ensure all generated code includes error handling: TRY/CATCH blocks in stored procedures, exception handling in PySpark, on_failure callbacks in Airflow. | In Scope |  | Med | 2
req_cg_030 | Run generated code through linting / static analysis pass before output (sqlfluff for SQL, pylint/ruff for Python). | In Scope |  | Med | 2 |  |  | Automated as post-generation step; report violations if any
PROMPT ENGINEERING & LLM ORCHESTRATION
req_cg_031 | Design modular, versioned prompt templates for each generation activity: DDL, DML, Spark codegen, DAG codegen, optimization analysis. | In Scope |  | High | 1 |  |  | Prompt library stored in repo; supports A/B testing of prompt variants
req_cg_032 | Implement structured output parsing (JSON schema enforcement) to ensure LLM output is machine-parseable and directly usable. | In Scope |  | High | 1 |  |  | Pydantic models for each output type; retry on parse failure
req_cg_033 | Implement context window management: chunking large schemas, summarizing upstream context, progressive detail injection for complex transformations. | In Scope |  | High | 2 |  |  | Critical for large models with 100+ tables
req_cg_034 | Implement few-shot examples library for each code generation pattern (SCD-2, incremental merge, pivot, unpivot, etc.). | In Scope |  | Med | 2 |  |  | Curated examples improve output quality significantly
req_cg_035 | Fine-tune prompts for each target platform dialect to avoid cross-platform syntax errors. | In Scope | req_cg_013 | Med | 3
AGENT ORCHESTRATION & EXECUTION
req_cg_036 | Run all code generation modules end-to-end in sequence or allow individual module re-runs via CLI (--module=ddl, --module=optimize, --module=all). | In Scope |  | High | 1 |  |  | CLI interface with module selection
req_cg_037 | Implement idempotent execution: re-running agent on same input produces same output unless config changes. | In Scope |  | Med | 2 |  |  | Deterministic seed for LLM calls; cached intermediate results
req_cg_038 | Log all agent decisions, prompt-response pairs, and intermediate artifacts for auditability and debugging. | In Scope |  | Med | 2 |  |  | Structured JSON logs; supports replay for debugging
req_cg_039 | Implement configurable retry and fallback logic when LLM responses fail validation or parsing. | In Scope |  | Med | 2 |  |  | Max 3 retries with escalating prompt specificity
req_cg_040 | Ensure agent stays within safe, compliant and governed boundaries — no execution of generated code against live databases, no credential handling. | In Scope |  | High | 1 |  |  | Guardrails: code generation only, never code execution
OUTPUT & HANDOFF
req_cg_041 | Output all generated code as files organized in a standard project structure (models/, dags/, tests/, docs/) ready for Git commit. | In Scope |  | Med | 1 |  |  | Matches dbt project structure conventions
req_cg_042 | Generate human-readable summary report of all code produced: what was generated, key decisions, optimization changes applied, flagged concerns. | In Scope |  | Med | 2 |  |  | Markdown report; serves as PR description
req_cg_043 | Define pass/fail acceptance criteria for each generated artifact — compilable SQL, valid DAG structure, no lint errors, all required columns present. | In Scope |  | Med | 1 |  |  | Automated validation gate before output
req_cg_044 | Push generated code directly to a Git branch and create a pull request via GitHub/GitLab API. | Out of Scope | [5 empty] | Deferred — MVP outputs to local filesystem; Git integration in Phase 2
req_cg_045 | Integrate output handoff to the Testing POD agent for automated test case generation against produced code. | In Scope | Testing POD | Med | 3 |  |  | API or file-based handoff; testing POD consumes generated artifacts

## SelfReview_Agent_Reqs
POD | Data Engineering Hub - Self-Review Agent
Agent Name | DE_SelfReview_Agent
Owner | Rakesh + Elan + Vamsee
Resources | Varun, Sanay
Description | Automated code review agent that validates generated code for correctness, performance, security, standards compliance, and completeness before human review or handoff.
# | Requirements Description | In Scope / Out of Scope | Dependency Requirement # | LOE (High/ Med / LOW) | MVP (1-4) | Planned St.Dt | Planned End Dt | Comments
CORRECTNESS VALIDATION
req_sr_001 | Validate generated DDL covers ALL tables, columns, data types, primary keys, and foreign keys defined in the approved data model — no missing or extra objects. | In Scope | req_cg_007 | High | 1 |  |  | Cross-reference model spec vs. generated DDL; report gaps
req_sr_002 | Validate generated DML/transformation logic implements every source-to-target mapping — no missing columns, no unmapped fields. | In Scope | req_cg_008 | High | 1 |  |  | Column-level traceability check
req_sr_003 | Verify SQL syntax correctness by parsing against target dialect grammar (Snowflake, BigQuery, etc.) without executing. | In Scope | req_cg_013 | High | 1 |  |  | sqlglot or sqlparse for syntax tree validation
req_sr_004 | Verify PySpark code syntax and structure via AST parsing — no undefined variables, no import errors, no type mismatches in DataFrame operations. | In Scope | req_cg_009 | High | 1 |  |  | Python AST + PySpark-specific checks
req_sr_005 | Validate Airflow DAG definitions have no circular dependencies, all tasks are reachable, schedule expressions are valid cron syntax. | In Scope | req_cg_011 | Med | 2 |  |  | DAG graph analysis for cycles and orphan tasks
req_sr_006 | Validate dbt model dependencies: all ref() calls point to existing models, no circular refs, proper staging>mart layering. | In Scope | req_cg_010 | Med | 2 |  |  | Simulates dbt compile --parse-only behavior
req_sr_007 | Check all generated data quality tests are syntactically correct and aligned to the columns they reference. | In Scope | req_cg_012 | Med | 2
PERFORMANCE REVIEW
req_sr_008 | Flag SQL anti-patterns: SELECT *, implicit cross joins, correlated subqueries, non-sargable predicates, missing WHERE clauses on large tables. | In Scope |  | High | 1 |  |  | Configurable rule set; severity: critical, warning, info
req_sr_009 | Validate partitioning and clustering keys in DDL align with query patterns in the DML transformations. | In Scope | req_cg_017, req_cg_018 | Med | 2 |  |  | Cross-file analysis: DDL partition key should match DML filter columns
req_sr_010 | Flag PySpark transforms that collect() to driver unnecessarily, use Python UDFs where built-ins exist, or shuffle excessively. | In Scope | req_cg_009 | Med | 2
req_sr_011 | Estimate relative cost of generated queries and flag any exceeding configurable thresholds. | In Scope |  | Low | 3 |  |  | Heuristic scoring; not actual warehouse cost
req_sr_012 | Integrate with actual EXPLAIN plan output from the target warehouse to compare estimated vs. actual performance. | Out of Scope | [5 empty] | Requires live warehouse access; deferred
SECURITY & COMPLIANCE REVIEW
req_sr_013 | Detect hardcoded credentials, connection strings, API keys, or secrets in any generated code. | In Scope |  | High | 1 |  |  | Regex + entropy-based secret detection; FAIL if found
req_sr_014 | Verify PII columns identified in data model have appropriate masking, hashing, or encryption in transformation logic. | In Scope | Testing POD PII scope | High | 1 |  |  | Cross-reference PII tags from model with transformation output
req_sr_015 | Check generated code does not expose raw PII in logs, error messages, or intermediate staging tables without masking. | In Scope |  | Med | 2
req_sr_016 | Validate role-based access control (GRANT/REVOKE) statements are included for sensitive tables and views. | In Scope |  | Med | 3 |  |  | Checks for GRANT statements; warns if missing on PII tables
req_sr_017 | Perform SAST on generated Python code for injection vulnerabilities, unsafe deserialization, etc. | Out of Scope | [5 empty] | Deferred to security team toolchain integration
STANDARDS COMPLIANCE REVIEW
req_sr_018 | Validate naming conventions across all generated artifacts match configured standards. | In Scope | req_cg_024 | Med | 1 |  |  | Configurable regex patterns per object type
req_sr_019 | Verify all generated files contain required header documentation (purpose, author, source, target, refresh strategy). | In Scope | req_cg_025 | Low | 2
req_sr_020 | Verify SQL formatting compliance against configured sqlfluff rules. | In Scope | req_cg_026 | Low | 2
req_sr_021 | Check NULL handling is explicit everywhere — no implicit NULL propagation in JOINs, aggregations, CASE statements, or WHERE clauses. | In Scope | req_cg_028 | Med | 1 |  |  | Flags bare column references in JOIN conditions without COALESCE/IS NOT NULL
req_sr_022 | Validate error handling patterns are present in stored procs, PySpark, and Airflow DAGs. | In Scope | req_cg_029 | Med | 2
COMPLETENESS & CONSISTENCY REVIEW
req_sr_023 | Verify code manifest lists every generated file and every listed file actually exists in output directory. | In Scope | req_cg_027, req_cg_041 | Low | 2 |  |  | Bi-directional check: manifest <> filesystem
req_sr_024 | Validate cross-file consistency: table names in DML exist in DDL; model names in DAGs exist in dbt project; test targets exist. | In Scope |  | High | 1 |  |  | Dependency graph construction across all output files
req_sr_025 | Ensure no orphan code: every generated SQL file referenced by at least one DAG task or dbt model. | In Scope |  | Med | 2
req_sr_026 | Verify incremental load logic includes proper watermark handling (high-water-mark column, last_loaded_timestamp). | In Scope |  | Med | 2 |  |  | Critical for correctness of incremental pipelines
req_sr_027 | Check SCD Type-2 implementations include all required fields: surrogate key, effective_from, effective_to, is_current flag. | In Scope |  | Med | 2
REVIEW OUTPUT & REPORTING
req_sr_028 | Produce structured review report with PASS/FAIL verdict per file and per check category (correctness, performance, security, standards, completeness). | In Scope |  | High | 1 |  |  | JSON + Markdown; machine-readable and human-readable
req_sr_029 | Assign severity to each finding: CRITICAL (blocks deployment), WARNING (should fix), INFO (best practice suggestion). | In Scope |  | Med | 1
req_sr_030 | Generate actionable fix suggestions for each finding with corrected code snippets. | In Scope |  | High | 2 |  |  | LLM-generated fix suggestions; high-value differentiator
req_sr_031 | Support auto-fix mode for low-risk deterministic issues (formatting, naming, missing comments) — apply fixes and report changes. | In Scope |  | Med | 3 |  |  | Only for safe, reversible fixes; never auto-fix logic changes
req_sr_032 | Provide overall quality score (0-100) based on weighted check results to track improvement over time. | In Scope |  | Low | 3 |  |  | Configurable weights per category
req_sr_033 | Integrate review findings into GitHub/GitLab PR comments automatically. | Out of Scope | [5 empty] | Deferred to Git integration phase
AGENT ORCHESTRATION & GUARDRAILS
req_sr_034 | Run full self-review pipeline end-to-end or allow individual review modules via CLI (--check=correctness, --check=performance, --check=all). | In Scope |  | High | 1
req_sr_035 | Design modular, versioned prompt templates for each review category. | In Scope |  | High | 1 |  |  | Stored in prompt library alongside codegen prompts
req_sr_036 | Log all review decisions, findings, and LLM interactions for auditability. | In Scope |  | Med | 2
req_sr_037 | Ensure self-review agent NEVER modifies original generated code (read-only) unless auto-fix mode is explicitly enabled. | In Scope |  | High | 1 |  |  | Guardrail: review is non-destructive by default
req_sr_038 | Define pass/fail acceptance criteria: minimum check coverage executed, no CRITICAL findings for PASS verdict. | In Scope |  | Med | 1

## Scope
Category | Key Features | Description
Input Parsing | Data model & architecture consumption | Accepts approved output from the Data Design POD (ERD, DDL specs, pipeline architecture, tech stack) and parses it into a structured representation for downstream code generation modules.
SQL DDL Generation | Table creation & schema definition | Generates CREATE TABLE, ALTER TABLE statements for target platform with correct data types, constraints, partition keys, clustering keys, and platform-specific syntax.
SQL DML Generation | Transformation & load logic | Generates SELECT, INSERT, MERGE/UPSERT queries implementing source-to-target mappings, SCD patterns, incremental loads, and business transformation rules.
PySpark Generation | Large-scale & streaming transforms | Generates PySpark scripts using DataFrame API and Structured Streaming for workloads that exceed SQL capabilities or require programmatic logic.
dbt Model Generation | Analytics engineering models | Generates dbt .sql model files with ref()/source() macros, schema.yml with tests and documentation, following staging > intermediate > marts layering.
DAG Generation | Pipeline orchestration | Generates Airflow DAG definitions with task dependencies, retry logic, SLA monitoring, sensors for data availability, and parameterized scheduling.
DQ Test Generation | Data quality assertions | Generates data quality check code (Great Expectations, dbt tests, custom SQL assertions) covering schema validation, null checks, referential integrity, and row counts.
Query Optimization | SQL & Spark performance tuning | Analyzes generated code for anti-patterns, recommends partitioning/clustering strategies, optimizes join order, eliminates redundant transformations, and estimates relative cost.
Self-Review: Correctness | Structural & logic validation | Validates DDL completeness against data model, DML mapping coverage, SQL syntax per dialect, DAG acyclicity, and dbt dependency integrity.
Self-Review: Performance | Anti-pattern detection | Flags SELECT *, unnecessary subqueries, missing predicates, excessive shuffles, and validates partitioning alignment with query patterns.
Self-Review: Security | Secrets & PII protection | Detects hardcoded credentials, verifies PII masking in transformations, checks for PII leakage in logs and staging, validates access control statements.
Self-Review: Standards | Naming & formatting compliance | Validates naming conventions, documentation headers, SQL formatting, NULL handling, and error handling patterns across all generated artifacts.
Self-Review: Completeness | Cross-file consistency | Verifies manifest accuracy, cross-file references, no orphan code, proper incremental watermarking, and SCD-2 field completeness.
Review Reporting | PASS/FAIL verdict & fix suggestions | Produces structured review reports with severity-classified findings, actionable fix suggestions with code snippets, and overall quality scores.

## RAID
RAID = | Risks, Assumptions, Issues and Dependencies.
Area | Type | Title | Details | Owner | Target Date | Resolve Date | Status and Notes
Code Generator | Risk | Data Design output format instability | If Data Design POD changes their output schema, our parser breaks. Need a stable contract. | Rakesh |  |  | Open — need versioned interface contract
Code Generator | Dependency | Data Design POD must deliver approved model first | Code generation is blocked until validated data model and pipeline architecture are received. | Elan |  |  | Dependency on Data_Design req_001 through req_005
Code Generator | Assumption | Target platform is known at generation time | Tech stack recommendation from Design POD is finalized; no mid-generation platform switch. | Vamsee
Code Generator | Risk | LLM output quality variance | Claude may generate syntactically correct but semantically wrong SQL for complex business rules. | Rakesh |  |  | Mitigated by self-review agent + few-shot examples
Code Generator | Assumption | No live database access required for MVP | Agent generates code against schemas, not live data. No EXPLAIN plans, no test execution. | Elan
Self-Review | Risk | False positives in security checks | Secret detection regex may flag legitimate config values as credentials. | Varun |  |  | Need tunable sensitivity levels
Self-Review | Dependency | Testing POD scope categories for DQ alignment | Self-review DQ checks must align with Testing POD categories. | Rakesh |  |  | Dependency on Testing POD Scope document
Self-Review | Issue | No cross-dialect syntax validator available offline | sqlglot covers most dialects but has gaps for newer Snowflake/BigQuery syntax. | Sanay |  |  | Investigating sqlglot + custom rule patches
Overall | Assumption | Claude API availability and rate limits sufficient | Stable API access with enough throughput for iterative code generation and review. | Rakesh
Overall | Risk | Context window limits for large schemas | Models with 100+ tables may exceed context window, causing incomplete generation. | Elan |  |  | Mitigated by chunking strategy in req_cg_033

## TechStack
Tools | Description | US/India/Both
Claude API (Anthropic) | Core LLM for code generation, optimization suggestions, and self-review analysis | Both
Python 3.11+ | Agent runtime, orchestration, prompt management, and CLI interface | Both
sqlglot | SQL parsing, transpilation across dialects, and syntax validation | Both
sqlfluff | SQL linting and formatting enforcement | Both
Pydantic | Structured output validation and schema enforcement for LLM responses | Both
Jinja2 | Template engine for prompt templates and code templates | Both
Click / Typer | CLI framework for agent module execution | Both
pytest | Unit and integration testing of agent modules | Both
GitHub / GitLab | Source code management for generated artifacts and agent code | Both
Docker | Containerized execution environment for consistent runs | Both