## Sprint_Plan
POD | Data Engineering Hub - Code Generator & Optimizer + Self-Review Agent
MVP-1 Scope | Input Parser + DDL Generator + DML Generator (BigQuery) + Basic Self-Review (Correctness + Security)
Sprint Duration | 2 weeks per sprint (10 working days)
MVP-1 Timeline | Apr 07 - May 01, 2026 (4 weeks / 2 sprints)
Team | Rakesh (Lead/Arch), Elan (Lead/LLM), Vamsee (Lead/Integration), Varun (Dev), Sanay (Dev)
Task ID | Task Description | Req Mapping | Assignee | Sprint | Start Date | End Date | Story Points | Dependencies | Status | Acceptance Criteria
SPRINT 1: FOUNDATION & INPUT PARSING (Apr 07 - Apr 17)
Project Setup & Infrastructure
T-001 | Initialize Git repo, project structure (models/, dags/, tests/, docs/), CI pipeline with linting | req_cg_041 | Sanay | S1 | Apr 07 | Apr 08 | 3 |  | Not Started | Repo created, pre-commit hooks for ruff+sqlfluff active, README with setup instructions
T-002 | Set up FastAPI skeleton with /api/v1/generate endpoint, request validation, health check | req_cg_036 | Vamsee | S1 | Apr 07 | Apr 09 | 5 |  | Not Started | POST /generate returns 202 with job_id; GET /status returns job state; Swagger docs auto-generated
T-003 | Set up Docker + docker-compose for local dev environment with all dependencies | N/A | Sanay | S1 | Apr 08 | Apr 09 | 3 | T-001 | Not Started | docker-compose up starts API server, all tests pass inside container
T-004 | Configure structlog JSON logging, request tracing with correlation IDs | req_cg_038 | Varun | S1 | Apr 08 | Apr 09 | 2 | T-001 | Not Started | Every API request logged with request_id, module, duration; logs parseable by jq
T-005 | Set up Claude API client wrapper with retry logic (exponential backoff), rate limit handling | req_cg_039 | Elan | S1 | Apr 07 | Apr 09 | 5 |  | Not Started | Client retries 3x on 429/timeout; structured logging of all prompt/response pairs; unit tests for retry behavior
Input Parser Module
T-006 | Define Pydantic models for input schema: DataModel, Table, Column, PipelineArchitecture, TechStack, TransformationRule | req_cg_001, req_cg_032 | Rakesh | S1 | Apr 07 | Apr 09 | 5 |  | Not Started | All models validate sample payload from Data Design POD; reject malformed input with clear error messages
T-007 | Build Input Parser module: consume API payload, validate version, hydrate internal TableSpec[], PipelineSpec objects | req_cg_001, req_cg_002, req_cg_003 | Rakesh | S1 | Apr 09 | Apr 11 | 8 | T-006 | Not Started | Parser correctly processes 3 sample payloads (small/medium/large model); all fields mapped to internal objects
T-008 | Build transformation rule parser: extract business rules from structured YAML + natural language into actionable TransformRule objects | req_cg_004 | Varun | S1 | Apr 10 | Apr 12 | 5 | T-006 | Not Started | Parses 10 sample transformation rules; handles both SQL-expression and NL-description formats
T-009 | Coordinate with Data Design POD on API contract finalization; create mock server with 3 sample payloads | req_cg_001 | Vamsee | S1 | Apr 07 | Apr 10 | 3 |  | Not Started | API contract document agreed and signed off; mock payloads cover: simple (5 tables), medium (20 tables), complex (50+ tables)
Prompt Library Foundation
T-010 | Design prompt template architecture: Jinja2 templates with versioning, variable injection, output schema definitions | req_cg_031 | Elan | S1 | Apr 09 | Apr 11 | 5 |  | Not Started | Template loader resolves by module+dialect+version; variables injected safely; unit tests for template rendering
T-011 | Build DDL generation prompt template (BigQuery): system prompt, few-shot examples (partition, cluster, PII policy tags) | req_cg_031, req_cg_034 | Elan | S1 | Apr 11 | Apr 13 | 5 | T-010 | Not Started | Prompt generates valid BigQuery DDL for 3 sample tables; includes partition, clustering, column descriptions
T-012 | Build DML generation prompt templates: MERGE/SCD-2, incremental append, full refresh, deduplication patterns | req_cg_031, req_cg_034 | Elan | S1 | Apr 13 | Apr 15 | 8 | T-010 | Not Started | Each pattern has system prompt + 2 few-shot examples; output matches Pydantic schema; tested against 5 transformation scenarios
DDL Generator Module
T-013 | Build DDL Generator: consume TableSpec[], generate BigQuery CREATE TABLE with partitioning, clustering, OPTIONS(description) | req_cg_007 | Rakesh | S1 | Apr 11 | Apr 14 | 8 | T-007, T-011 | Not Started | Generates valid DDL for all tables in medium sample payload; sqlglot parses without errors; partition/cluster keys match spec
T-014 | Add PII handling to DDL: column-level policy tags, GRANT statements for sensitive columns | req_cg_007 | Varun | S1 | Apr 14 | Apr 15 | 3 | T-013 | Not Started | PII-flagged columns get policy tag annotations; GRANT statements generated for each PII table
T-015 | Add naming convention enforcement: snake_case validation, layer prefix injection (stg_, fct_, dim_), dataset prefixes | req_cg_024 | Sanay | S1 | Apr 13 | Apr 15 | 3 | T-013 | Not Started | Naming config loaded from YAML; violations auto-corrected; unit tests for 15 naming edge cases
T-016 | DDL Generator integration tests: end-to-end from API payload to DDL file output for all 3 sample payloads | req_cg_007, req_cg_043 | Rakesh | S1 | Apr 15 | Apr 16 | 3 | T-013, T-014, T-015 | Not Started | All 3 payloads produce valid DDL; sqlglot BigQuery dialect parse passes; no lint errors
SPRINT 2: DML GENERATOR & BASIC SELF-REVIEW (Apr 20 - May 01)
DML / Transformation Generator Module
T-017 | Build DML Generator core: consume PipelineSpec + TransformRules, route to correct pattern (full refresh, incremental, SCD-1, SCD-2) | req_cg_008 | Rakesh | S2 | Apr 20 | Apr 23 | 8 | T-007, T-012 | Not Started | Pattern router correctly identifies refresh strategy for each table; generates correct SQL template per pattern
T-018 | Implement SCD Type-2 MERGE generation: surrogate key (FARM_FINGERPRINT), effective_from/to, is_current, hash diff comparison | req_cg_008 | Elan | S2 | Apr 20 | Apr 23 | 8 | T-012 | Not Started | SCD-2 MERGE SQL passes sqlglot validation; correctly handles: new inserts, updates (close+insert), no-change skip
T-019 | Implement incremental append generation: high-water-mark pattern with _loaded_at, deduplication with ROW_NUMBER/QUALIFY | req_cg_008 | Varun | S2 | Apr 21 | Apr 23 | 5 | T-012 | Not Started | Incremental SQL correctly references watermark column; QUALIFY dedup logic validated on sample data
T-020 | Add NULL handling enforcement: COALESCE wrappers on outer join columns, IS NOT NULL guards in join conditions | req_cg_028 | Sanay | S2 | Apr 23 | Apr 24 | 3 | T-017 | Not Started | Post-processing pass adds COALESCE to all LEFT/RIGHT/FULL JOIN output columns; unit tests for 8 join patterns
T-021 | Add inline comments and file headers to all generated SQL: purpose, source, target, SCD type, refresh strategy, generated timestamp | req_cg_025 | Sanay | S2 | Apr 24 | Apr 25 | 2 | T-017 | Not Started | Every generated file has standardized header; comments before each CTE explain its purpose
T-022 | DML Generator integration tests: end-to-end for all 3 sample payloads covering all 4 transformation patterns | req_cg_008, req_cg_043 | Vamsee | S2 | Apr 24 | Apr 25 | 3 | T-017, T-018, T-019 | Not Started | All payloads produce valid DML; pattern assignment matches pipeline spec; sqlglot + sqlfluff pass
Self-Review Agent: Correctness Module
T-023 | Build correctness checker: DDL completeness validation (all model tables present, all columns, correct types, PKs, FKs) | req_sr_001 | Rakesh | S2 | Apr 23 | Apr 25 | 5 | T-016 | Not Started | Detects 100% of missing tables, missing columns, wrong data types in test payloads; zero false negatives on known-good output
T-024 | Build correctness checker: DML mapping coverage (every source-to-target mapping has corresponding SQL) | req_sr_002 | Varun | S2 | Apr 24 | Apr 26 | 5 | T-022 | Not Started | Reports unmapped columns with severity CRITICAL; traces each target column back to source column or transform rule
T-025 | Build SQL syntax validator: parse all generated SQL through sqlglot BigQuery dialect; report errors with line numbers | req_sr_003 | Sanay | S2 | Apr 24 | Apr 26 | 3 | T-016, T-022 | Not Started | Catches all intentionally broken SQL in test suite; zero false positives on valid BigQuery SQL
Self-Review Agent: Security Module
T-026 | Build secret detection: regex + entropy scan for credentials, API keys, connection strings in all generated files | req_sr_013 | Varun | S2 | Apr 25 | Apr 27 | 5 |  | Not Started | Detects all 12 test secret patterns (AWS keys, GCP service account JSON, passwords, tokens); fewer than 5% false positive rate
T-027 | Build PII masking validator: cross-reference data model PII flags with generated SQL to verify masking/hashing applied | req_sr_014 | Elan | S2 | Apr 25 | Apr 27 | 5 | T-013, T-017 | Not Started | Flags every PII column that appears unmasked in output SQL; reports CRITICAL for raw PII in SELECT output
Review Report & Output Packaging
T-028 | Build review verdict engine: aggregate findings by severity, apply PASS/CONDITIONAL PASS/FAIL logic, generate JSON + Markdown report | req_sr_028, req_sr_029 | Vamsee | S2 | Apr 26 | Apr 28 | 5 | T-023, T-024, T-025, T-026, T-027 | Not Started | Report correctly classifies: PASS (no findings), CONDITIONAL (warnings only), FAIL (any critical); Markdown readable by humans
T-029 | Build output packager: organize DDL + DML files in project structure, generate MANIFEST.json with file inventory and hashes | req_cg_041, req_cg_027 | Sanay | S2 | Apr 26 | Apr 28 | 3 | T-016, T-022 | Not Started | Output directory matches spec from architecture doc Section 8; MANIFEST lists every file with SHA-256 hash
T-030 | Build CLI interface: typer-based CLI with --module flag (parse, ddl, dml, review, all) and --auto-fix stub | req_cg_036, req_sr_034 | Vamsee | S2 | Apr 27 | Apr 28 | 3 | T-028, T-029 | Not Started | CLI runs full pipeline end-to-end; individual modules runnable independently; --help documents all options
MVP-1 Integration & Demo
T-031 | End-to-end integration test: Data Design mock API call → parse → DDL gen → DML gen → self-review → output package | All MVP-1 reqs | Rakesh | S2 | Apr 28 | Apr 29 | 5 | T-030 | Not Started | Full pipeline completes for all 3 sample payloads; review verdict matches expected result; output directory valid
T-032 | MVP-1 demo preparation: walkthrough script, sample inputs, expected outputs, known limitations document | N/A | Vamsee | S2 | Apr 28 | Apr 29 | 2 | T-031 | Not Started | Demo script covers happy path + error handling; limitations doc lists all Out of Scope items with rationale

## Resource_Allocation
Resource Allocation by Sprint & Week
Resource | Role | S1-Wk1 Focus | S1-Wk1 Pts | S1-Wk2 Focus | S1-Wk2 Pts | S2-Wk1 Focus | S2-Wk1 Pts | S2-Wk2 Focus | S2-Wk2 Pts | Total Pts
Rakesh | Lead / Architect | Input Pydantic models, Input Parser module | 10 | DDL Generator core, DDL integration tests | 11 | DML Generator routing, Correctness checker (DDL) | 13 | E2E integration test, Demo prep | 7 | 41
Elan | Lead / LLM | Claude API client, Prompt template architecture | 10 | DDL prompt template, DML prompt templates | 13 | SCD-2 MERGE generation, PII masking validator | 13 | Prompt iteration & tuning (buffer) | 5 | 41
Vamsee | Lead / Integration | FastAPI skeleton, Data Design POD contract | 8 | Mock server, API testing | 5 | DML integration tests, Review verdict engine | 8 | CLI interface, Output packager, Demo prep | 8 | 29
Varun | Developer | Logging setup, Transformation rule parser | 7 | PII handling in DDL | 3 | Incremental append gen, DML mapping coverage checker | 10 | Secret detection module | 5 | 25
Sanay | Developer | Git repo setup, Docker setup | 6 | Naming convention enforcement | 3 | NULL handling, File headers, SQL syntax validator | 8 | Output packager, MANIFEST gen | 3 | 20

## MVP_Roadmap
MVP Phasing Roadmap — Full Scope
Phase | Sprint(s) | Timeline | Deliverables | Success Criteria | Team Focus
MVP-1 | S1-S2 | Apr 07 - May 01 | Input Parser + DDL Generator + DML Generator (BigQuery) + Basic Self-Review (Correctness + Security) + CLI + Output Packager | Given a sample data model from Data Design POD, agent generates valid BigQuery DDL and DML that passes syntax validation, correctness review, and security scan. | Rakesh: Parser+DDL+DML core; Elan: Prompts+LLM; Vamsee: API+CLI+Integration; Varun: Transform rules+Security; Sanay: Infra+Standards
MVP-2 | S3-S4 | May 04 - May 29 | dbt Model Generator + Airflow DAG Generator + Optimization Engine (BigQuery anti-patterns, partitioning, clustering) | Complete dbt project and Airflow DAGs generated from same input. Optimization pass identifies and fixes at least 5 anti-pattern categories. | Rakesh: dbt gen; Elan: Optimization prompts; Vamsee: DAG gen; Varun+Sanay: Optimization rules
MVP-3 | S5-S6 | Jun 01 - Jun 26 | Full Self-Review (Performance + Standards + Completeness) + Auto-Fix + Quality Scoring + Testing POD API handoff | End-to-end pipeline: design in, reviewed code out, handed to Testing POD via API. Quality score > 80 on sample inputs. | Rakesh: Review dims; Elan: Fix suggestion prompts; Vamsee: Testing POD integration; Varun+Sanay: Auto-fix engine
MVP-4 | S7-S8 | Jun 29 - Jul 24 | Multi-dialect support (Snowflake, Spark SQL) + PySpark Generator + DQ Test Generation + Knowledge POD handoff | Same data model generates code for BigQuery AND Snowflake. PySpark scripts for streaming workloads. DQ tests generated. | Full team: Dialect adapter, PySpark gen, Knowledge POD integration

## Velocity_Metrics
Sprint Velocity Targets
Metric | Sprint 1 Target | Sprint 2 Target | Notes
Total Story Points | 76 | 80 | Sprint 1 is foundation-heavy; Sprint 2 is feature-heavy
Tasks Planned | 16 | 16 | Balanced task count across sprints
Tasks per Dev (avg) | 3.2 | 3.2 | 5 team members, ~3 tasks each
Points per Dev (avg) | 15.2 | 16.0 | Leads carry higher points due to complex tasks
Bug Buffer (%) | 10% | 15% | Higher buffer in Sprint 2 due to integration complexity
Demo / Review Day | Apr 17 | May 01 | Sprint review + retrospective on last day
Key Risk: Sprint 1 | Data Design POD contract delay |  | Mitigation: T-009 mock server enables parallel development
Key Risk: Sprint 2 | SCD-2 MERGE prompt quality |  | Mitigation: T-012 few-shot examples; 2 retry passes allowed
Definition of Done | Code reviewed, tests pass, acceptance criteria met, docs updated |  | Every task must meet all 4 criteria before marking complete